CASE STUDY
Preparation of a Software Project Plan

Scope, Timeline, and Team Roles for FitCheck Application

Aim

To formulate a comprehensive Software Project Plan covering project scope, execution timeline, and team resource allocation for a real-world software application.

Objective

- Define the operational and functional scope of the software application.

- Establish a structured timeline and Sprint-based execution schedule.

- Define team roles, responsibilities, and resource allocation.

- Create risk management strategies and milestone delivery schedules to ensure on-time project execution.

Selected Software Application

FitCheck (Smart Outfit Planner & Wardrobe Organizer)

Overview: FitCheck is an AI-powered smart wardrobe and outfit planning mobile application designed to digitize users' physical clothing items, automate daily outfit recommendations based on weather and style preference, and facilitate weekly outfit planning.

1. Project Scope

In-Scope (Functional Deliverables)

- User Authentication & Profiles: Secure registration, login, and user style preferences management.

- Wardrobe Digitization Module: Camera/gallery photo uploading, automatic background removal, and clothing categorization (Tops, Bottoms, Shoes, Accessories).

- AI Recommendation Engine: Rule-based and style-matching algorithms to build complete daily outfits synced with real-time local weather APIs.

- Interactive Calendar Planner: Interface enabling users to plan and assign outfits for future dates and occasions.

- Feedback Loop: Feature allowing users to like, dislike, or save generated outfit combinations.

Out-of-Scope (Future Releases)

- Direct e-commerce integration or purchasing items from third-party clothing retailers.

- Augmented Reality (AR) 'Virtual Try-On' using live camera feeds.

- Social media feeds or community sharing (reserved for post-v1 rollout).

2. Project Timeline & Sprint Breakdown

The project follows a 16-Week Agile Schedule, divided into 4-week phases and 2-week Sprints.

| Phase | Duration | Core Focus & Milestones | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Inception & Architecture | Weeks 1–4 | Requirements gathering, system architecture design, UI/UX wireframing, tech stack finalization. | SRS Document, Architecture Diagram, Figma Wireframes |
| Phase 2: Core Development | Weeks 5–8 | Sprint 1: Auth & Wardrobe Upload UI. Sprint 2: Image Background Removal API & Wardrobe Categorization DB. | Working User Module & Image Processing Pipeline |
| Phase 3: AI Integration & Planning | Weeks 9–12 | Sprint 3: Weather API integration & Style Recommendation Algorithm. Sprint 4: Weekly Outfit Calendar & Customization Module. | Functional Outfit Generator & Interactive Calendar |
| Phase 4: Testing & Deployment | Weeks 13–16 | System integration testing, UAT, bug fixes, App Store/Play Store setup, Cloud CI/CD deployment. | Production App Build, Live Cloud API, Final Project Report |

3. Team Roles and Responsibilities

| Role | Primary Responsibilities | Key Deliverables |
| --- | --- | --- |
| Project Manager / Scrum Master | Oversees timeline, sprint meetings, resource allocation, and risk management. | Project Plan, Sprint Backlog, Burndown Charts |
| UI/UX Designer | Designs app wireframes, user flows, and interactive mockups. | Figma Design System, Interactive Prototypes |
| Mobile App Developer (Flutter/React Native) | Builds cross-platform front-end features for iOS and Android. | Mobile Application Frontend Code |
| Backend & Cloud Engineer | Builds REST APIs, user databases, authentication services, and manages AWS infrastructure. | Database Schema, Server APIs, DevOps Pipelines |
| AI / ML Engineer | Develops image background removal service, auto-tagging, and style-matching recommendation logic. | Image Processing Pipeline, Recommendation Logic |
| QA / Software Tester | Writes test cases, performs unit/integration testing, and validates user flows. | Test Case Log, Bug Reports, UAT Sign-off |

4. Resource & Tools Allocation

- Design & Collaboration: Figma, Jira, Confluence.

- Frontend Development: Flutter / React Native, Dart / JavaScript.

- Backend & AI Logic: Node.js, Python (OpenCV/PyTorch for image tag processing).

- Database: MongoDB / PostgreSQL.

- Cloud Infrastructure & Tools: AWS Lambda, S3 Bucket (for image hosting), Supabase, GitHub Actions (CI/CD).

5. Risk Management Plan

| Risk Description | Severity | Mitigation Strategy |
| --- | --- | --- |
| Delay in AI image background removal processing time | High | Integrate lightweight pre-trained cloud vision APIs before building custom models. |
| Inaccurate weather API data causing wrong suggestions | Medium | Implement fallback default weather rules based on seasonal temperature averages. |
| Scope Creep due to adding social features early | Medium | Enforce strict MVP boundary; move non-essential features to Phase 2 backlog. |

Results

- The structured project plan establishes a clear 16-week path from initial requirements to production deployment.

- Defining clear team roles ensures distinct accountability across mobile development, AI processing, and cloud deployment.

- Sprint-based execution guarantees iterative testing of critical components (e.g., wardrobe uploads and recommendation logic) before app store launch.

Conclusion

A well-defined software project plan is crucial for turning conceptual applications like FitCheck into functional, production-ready software. By organizing the development process into structured Agile Sprints, mapping core team competencies, and enforcing a clear scope, the development team can mitigate technical risks, manage resources efficiently, and deliver a reliable smart wardrobe application on schedule.